## Sheet1
No. | Task name | Status | Start day | End day | Duration (days) | Comments | Description
1 | Investigate UART IP specification |  | 6th July | 8th July
| Investigate introduction | Finish |  |  | 0.5 day |  | Read and understand Introduction, Block Diagram, Feature.
| Investigate submodules and signals function | Finish |  |  | 0.5 day |  | Understand each signals function and how each modules work.
| Investigate registers' function | Finish |  |  | 1 day |  | Understand how to setting register for DUT operations.
2 | Estimate planning |  | 8th July | 9th July
| Create Planning | Finish |  |  | 1 day |  | Determine the overall project timeline, develop a detailed plan for each task, and estimate the required time based on the complexity of each task.
3 | Create V-Plan |  | 9th July | 11th July
| V-Plan item definition | On progress |  |  | 1 day |  | Brainstorm ideas and identify potential items to be included in the verification plan (VPlan).
| Test Scenario Development | On progress |  |  | 2 days |  | Define detailed test scenarios for each verification item, specifying input/output values, expected results, and the necessary register configurations to prepare the DUT before testing.
4 | Draw testbench structure |  | 8th July | 9th July
| VIP Architecture Design | On progress |  |  | 0.5 day |  | Identify all required Verification IPs (VIPs) and UVM agents needed to build a complete verification environment.
| Verification Environment Integration | On progress |  |  | 0.5 day |  | Integrate all Verification IPs (VIPs) and UVM agents to build a complete verification environment, including interface connections, DUT integration, TLM communication, and the overall testbench architecture.
5 | Build testbench |  | 9th July | 18th July
| Build uvm structure | On progress |  |  | 2 days |  | Develop AHB and UART UVM agents, including sequencers, drivers, monitors, interfaces, and scoreboards.
| Checking classes' connection error | On progress |  |  | 2 days |  | Integrate the AHB and UART UVM agents with the verification environment by connecting the drivers to the DUT, the monitors to the DUT interfaces, and the monitors' analysis ports to the scoreboard.
| Build uvm envrironment | On progress |  |  | 2 days |  | Develop the UVM environment by instantiating and configuring all verification components, enabling communication between agents, and supporting reusable test execution.
| Prepare Script | On progress |  |  | 1 day |  | Create Script for simulation and debug
| Create Register Model (RAL) | On progress |  |  | 2 days |  | Develop the UVM RAL model for all DUT registers, including register definitions, fields, address mapping, and bus integration.
6 | Create sequence, test scenario and checker |  | 18th July | 30th July
| Create base test and register test | On progress |  |  | 1 day |  | Create Base test and Register Test base on RAL
| Create sequences | On progress |  |  | 7 days |  | Create seqeunces for each TESTs
| Create UART_RXD test | On progress |  |  | 1 days |  | Create UART_RXD testcase base on UART_RXD sequence
| Create UART_TXD test | On progress |  |  | 1 days |  | Create UART_TXD testcase base on UART_TXD sequence
| Create Interrupt test | On progress |  |  | 1 days |  | Create Interrupt testcase base on Interrupt sequence
| Create Error Handling test | On progress |  |  | 1 day |  | Create Error Handling testcase base on Error sequence
7 | Implement functional coverage |  | 30th July | 1st August
| Create coverpoint for every feature | On progress |  |  | 1 day |  | Develop functional covergroups and coverpoints to measure coverage for all DUT features, protocols, operating modes, and functional scenarios.
| Cross every coverpoint | On progress |  |  | 1 day |  | Create cross coverage between related coverpoints to verify feature interactions and ensure comprehensive functional coverage across all critical scenarios.
8 | Check regress report |  | 1st July | 3rd July
| Prepare regess.pl and regress.cfg files | On progress |  |  | 1 day |  | Prepare regress.pl file and regress.cfg to run all test case and report in only 1 file
| Check and fix error in regress rpt | On progress |  |  | 1 day |  | Check whether the report is right or not